|  | Deployment procedures for emergencies |
| --- | --- |

The following document sets out the roles and responsibilities for defining HR requirements and the activation of the internal and external rosters at the onset of a graded emergency. It should be read in conjunction with the Delegation of Authority outlined at WHO eManual XVII.6.1; the SOP on Defining HR Requirements and the SOPs on the deployment of internal, external, Stand-By Partnership and GOARN rosters (WHO eManual XVII.6.4).

| Phase | Steps | Responsible | Details | End Results |
| --- | --- | --- | --- | --- |
| Planning | Identify Incident Manager (IM) | WR/RED/ Director ARC/ EXD/WHE | - Establish IMST and pillar leads to manage the response - Prior to the IM being in function, another staff will be designated ad interim as designated by senior staff | - IM and pillar leads appointed - IMST functional |
|  | Define HR Requirements | (Grade 1, 2 or 3) IM – acute WR – protracted HR Team Lead HQ/ HR Manager in Region, Manager EMS HQ | - Designate HR Lead and support staff - Designate Finance Lead and support staff - Using standard IMS roles and TORs, develop an HR deployment plan and organogram with details of the location, role/function, grade, deployment modality, deployee, duration of deployment, inter/national deployment | - HR Plan defined - Work Plan defined - Funding secured - SEC/MEDEVAC defined |
|  | Confirm Budget and Funding | IM/WR and EMS Lead HQ | - Develop budget and defines funding requirements/gaps - IM to submit CFE request - Create Emergency Operations and Appeals (EOA) (previously known as OCR) HR workplans at all three levels where staff and non-staff positions will be managed - HQ: EMS to establish workplan structure and prepare award budgeting / HRT to create positions as per the approved workplans - Ensure availability of funding for ongoing emergency operations |  |
|  | Approve HR and Work Plan | WR (Grade 1, 2 or 3) RED & RD (Grade 2 or 3) EXD (Grade 3 and staff/non-staff HR plan for HQ for graded events) | - Finance/HR to submit a consolidated HR plan (as per prescribed template) with staff and non-staff functions for approval within 10–30 days. Any revision to the HR plan to be approved by EXD as and when required. |  |
|  | Define Security and medical requirements and administrative arrangements | IM/WR/AO/ WCO HR Lead SHW SEC AO/OO/BOA | - Designate SEC, SHW/ MEDEVAC, psycho-social support focal points - Designate PRSEAH focal point - Designate a focal point for visas, transportation, accommodation, HR - Security Risk is assessed and defined - Define scope and location of SHW and SEC briefings - Define scope and location of administrative/technical briefings - Establish communication mechanisms |  |
| Sourcing | Determine deployment priorities and confirm HR sourcing mechanisms | HR Lead* at the three levels | - Determine the priority needs and availability of deployments to be processed: - WCO/WHO staff and non-staff repurposed - GOARN Experts - Standby Partners - WHO External rosters | - Deployment phases and sourcing mechanisms defined |
|  | Identify candidates from various sourcing mechanisms | HR Lead at the three levels | - Collate the list with any identified internal and external candidates according to sourcing mechanisms: - Review CV/PHF and validate if the candidate meets the minimum criteria against the recommended function - Validate availability - Confirm that there is no flag in clear check |  |
|  | Recommend candidates | HR Lead at the three levels | - Assigned HR focal point compiles candidate lists and clears the candidates for deployment with the IM (for acute) WR (for protracted) in line with the DoA. |  |

*HR Lead for international deployment may be the RO or WHE HQ Focal Point. HR Lead for national deployment is the WCO HR Focal Point.

| Phase | Steps | Responsible | Details | End Results |
| --- | --- | --- | --- | --- |
| Selection & Deployment | Approve Candidates (Surge Capacity) | Acute: IM up to 3 months WR up to 6 months For HQ IMST: EXD to approve all staff/non-staff positions Protracted: WR Above 6 months: RD (Grade 1 and 2) or EXD (Grade 3) | - Establish IMST and pillar leads to manage the response - Prior to the IM being in function, another staff will be designated ad interim as designated by Senior Staff | - Surge capacity identified - Contract issued - Visa issued - Travel documents issued - Surge support ready for deployment |
|  | Inform Candidates (Surge Capacity) of decision to deploy | HQ HR Focal Point | - Alert candidates of potential deployment - Send standard message informing deployee of deployment details (if deployment dates differ from pre-approved dates, agreement will be sought from deployee and supervisor (for internal staff)) - Send regret message to candidates who are not deployed at that point |  |
|  | Prepare surge capacity for deployment and process recruitment (where applicable) and deployment formalities | HQ HR Focal Point | Initiate: - Duty travel for internal staff - Visa, UNLP and for consultants UN Certificates to facilitate entry - Recruitment/contracting of external candidates using temporary appointments under SR420.4/consultant contracts - HQ to deploy GOARN Experts - HQ to deploy Standby Partner Personnel - Ensure compliance to all pre-departure mandatory formalities - Notify event site of deployees’ arrival |  |
| Arrival at Event Site & Support during Deployment | Prepare event site for arrival of Surge Capacity | AO/OO/WCO HR Focal Point | - Confirm mechanism for exchanging information and reception of deployees - Ensure event site has adequate facilities for transportation and accommodation for emergency support - Provide visa support (AO/OO/WCO HR Focal Point) - Note Verbale for deployments from HQ and coordination with MOFA | - Surge capacity arrived and are briefed at the event site |
|  | Receive Surge Capacity at event site | WCO AO/OO | - Organize airport pick up and in-country flights and hotel accommodation |  |
|  | Brief and support Surge Capacity at event site | AO/OO/WCO HR Focal Point SEC/HSW Focal Points First level supervisor/manager | - Organize administrative and technical briefings - Discuss HR-related benefits and entitlements - Ensure deployees meet with line supervisors to discuss and agree on the TORs/deliverables - Ensure deployees receive information/support (including distribution of IT/electronic equipment) necessary to integrate into the emergency operations - Ensure deployees are included in Security plan |  |

| Phase | Steps |  | Responsible | Details | End Results |
| --- | --- | --- | --- | --- | --- |
| Monitoring HR Requirements | Extension of Deployment | Monitor HR requirements and recommend extensions | IM/WR/HR Lead | - Monitor HR requirements, including potential extensions/ separations - Discuss extension decision with deployee and if in agreement informs HRO/HR Focal point of extension decisions for relevant action | - Performance evaluation completed - End of Mission technical report submitted - Handover notes submitted - Deployment extended/finished - Roster updated - New HR requirements identified |
|  |  | Process extensions | HQ HR Focal Point/WCO/SBP or GOARN Technical Officers | - Initiate extension based on IM, WCO, RED request - Request for extensions based on DoA, memos requesting waivers for extension without selection - WCO manages extension of Visa if required - If extension involves a SBP Personnel or GOARN Expert, inform SBP partner or GOARN Secretariat and request confirmation to extend - Request for End of Mission report and Handover notes as applicable |  |
|  | End of Deployment | Monitor HR requirements and initiate end of deployment formalities | IM/WR/HR Lead | - Monitor HR requirements and discuss decision not to extend with line managers and deployees - Inform HR focal point of decision in order to initiate end of deployment actions |  |
|  |  | Performance Evaluation, End of Mission technical report and handover notes | 1st level supervisor/Manager | - Staff on duty travel: Note prepared to be included in ePMDS (prepared by 1st level supervisor) and handover notes and end of mission report (prepared by staff member) - Consultants: Performance Evaluation Form (PER) (prepared by manager) and end of mission report and handover notes, if applicable - Staff: PMDS notes - GOARN Experts: End of mission report, PER and handover notes, if applicable - SBP Personnel: End of mission report, PER and handover notes |  |
|  |  | Separation formalities | HR Team | - Ensure PER is made accessible to WHO managers for future deployments |  |